# Job Finder — 2-Week Task Planner

Editable DOCX version converted from the provided planner. This document contains the daily tasks and role assignments for the 14-day Job Finder project sprint.

## Day 1 — Mon · Kickoff

Phase: Project kickoff & environment setup

### Project Manager

Hold project kickoff meeting — present 2-week timeline, define scope, assign owners

Create requirements document: 3 roles (user/HR/admin), all screens, map feature, Firebase stack

Build risk register — flag map API complexity, Firestore indexing, 2-week tight schedule

Set up Trello board with 14 daily columns; populate Day 1–4 tasks immediately

Confirm acceptance criteria: what does 'done' look like for each feature by end of Week 2

### Scrum Master

Facilitate sprint planning: convert requirements into user stories with story points

Set up GitHub repo with branching strategy: main / dev / feature/xxx, add PR template

Create Definition of Done checklist: code reviewed, tested on device, Firestore connected

Schedule daily standup at 9 AM — 15 min max, same link every day

Install and walk the team through VS Code setup: Expo CLI, Firebase CLI, Prettier, ESLint

### UI/UX Developer 1

Install VS Code, Node.js, Expo Go app on phone; run expo init to bootstrap project

Add all dependencies: React Navigation (Stack + Drawer), Ionicons, expo-location

Create Figma project; build design system: navy #1e3a5f (user), purple #7c3aed (HR), red #dc2626 (admin)

Wireframe Login screen: hero banner, email/password fields, eye toggle, role info cards below

Share wireframes in team Discord for same-day feedback before implementation begins

### UI/UX Developer 2

Set up shared Figma component library: buttons, inputs, badges, status chips, avatar circles

Wireframe Register screen: role selector cards (user/HR), name + email + password + confirm fields

Wireframe Drawer/Sidebar layout for all 3 roles showing distinct color themes per role

Design app icon concept and splash screen (navy background, briefcase icon)

Document spacing tokens: 8px base unit, corner radius 12px (cards), 20px (pills)

### Backend Developer

Create Firebase project in console; enable Email/Password Auth and Firestore database

Install firebase SDK: npm install firebase in the Expo project

Write firebaseConfig.js: initializeApp, export auth and db instances

Design Firestore schema on paper: users {uid, email, displayName, role, isActive, profile, lat, lng}, jobs {title, company, location, lat, lng, type, salary, status, description, requirements, postedBy, applicantCount}, applications {jobId, userId, userName, userEmail, status, message, appliedAt}

Test Firebase connection: write a dummy doc to Firestore, confirm it appears in console

### Quality Assurance

Write master test plan: scope (3 roles × all screens), environments (Android + iOS + Web)

Create test case spreadsheet with columns: ID, screen, action, expected result, actual, pass/fail

Set up two physical test devices (or emulators): Android API 30+, iOS 15+

Write Day 2 auth test cases in advance: valid login, wrong password, unregistered email, empty fields

Configure Expo Go on test devices; verify team can share dev build via QR code

## Day 2 — Tue · Auth

Phase: Login, register screens & Firebase auth

### Project Manager

Review Day 1 Figma wireframes with UI/UX team — sign off before implementation starts

Verify GitHub repo structure is correct; ensure all team members have push access

Track Day 1 vs Day 2 progress on Trello — flag any blocked tasks immediately

Write stakeholder brief: project overview, team roles, 2-week delivery date

Confirm Firebase project billing plan (Spark free tier is sufficient for this project)

### Scrum Master

Run first daily standup — each member: done/doing/blocked in 2 min

Update sprint board: move Day 1 tasks to Done, add Day 2 tasks to In Progress

Confirm UIUX1 and BE are aligned on firebaseConfig.js export before UIUX1 imports it

Remove blocker: if BE hasn't finished AppContext auth, UIUX1 can use mock login() for now

Document standup notes in Discord #standup channel for async team members

### UI/UX Developer 1

Implement LoginScreen.js: navy hero with briefcase logo, email input, password with eye toggle

Add role info cards at bottom of Login (color-coded: blue=user, purple=HR, red=admin)

Wire login button to login() from AppContext; show ActivityIndicator while loading

Add Alert on failed login with error message from Firebase (wrong password, user not found)

Test login flow on device with Expo Go — verify keyboard avoidance works on both iOS and Android

### UI/UX Developer 2

Implement RegisterScreen.js: back button, role selector (User / HR as toggle cards)

Build form fields: Full Name, Email, Password, Confirm Password with eye toggle

Add password validation: min 6 chars, mismatch check before calling register()

Wire Create Account button to register() from AppContext; navigate to role drawer on success

Test register screen on device — verify role selector visually highlights the active choice

### Backend Developer

Implement AppContext.js: createContext, AppProvider wrapper, useApp() hook

Add login(email, password): signInWithEmailAndPassword + isActive guard + error return

Add register(email, password, name, role): createUserWithEmailAndPassword + saveUserToFirestore()

Add logout(): signOut(auth)

Implement onAuthStateChanged listener: fetch Firestore user profile, set role state, setIsAuthLoading(false) when done

## Day 3 — Wed · Navigation

Phase: Role-based navigation & sidebar drawer

### Project Manager

Check if auth screens are fully working end-to-end before navigation work begins

Review navigation architecture with Scrum Master — confirm drawer vs stack approach

Update risk log: confirm expo-location will be added Day 5, alert team to prepare

Mid-week team morale check — 2 weeks is intense; confirm everyone is on pace

Send progress update message to instructor/stakeholder: auth complete, navigation in progress

### Scrum Master

Standup: verify auth is done (UIUX1+UIUX2+BE all green) before navigation starts

Coordinate: BE must finish AppContext role state before UIUX2 can build role-aware drawer

Update Trello: auth stories to Done, navigation stories to In Progress

Resolve any Expo version conflicts surfaced from Day 2 installs

Remind team: no skipping QA testing — every screen must be tested on device before Day 4

### UI/UX Developer 1

Implement DrawerContent.js: avatar initials circle (first letter of name), display name, email

Add role badge in DrawerContent (color-coded label: Job Seeker / HR Manager / Administrator)

Build menu item list with Ionicons: map role → menu items array, render TouchableOpacity rows

Add chevron-forward arrow on each menu item; highlight selected route

Add logout button at bottom with red icon; wire to logout() with Alert confirmation

### UI/UX Developer 2

Implement UserDrawer.js: Drawer.Navigator wrapping Home, MyApplications, Profile screens

Implement HRDrawer.js: wrapping HRDashboard, PostJob, ManageApplications, Profile

Implement AdminDrawer.js: wrapping AdminDashboard, ManageUsers, Profile

Set header colors per role: navy for user, purple for HR, red for admin

Implement AppNavigator.js: if !currentUser → Auth Stack; if role=admin → AdminDrawer; if hr → HRDrawer; else UserDrawer

### Backend Developer

Export userRole from AppContext so AppNavigator can conditionally render correct drawer

Ensure fetchUserProfile() is called inside onAuthStateChanged and role is set before isAuthLoading=false

Test role routing: create 3 test accounts in Firestore with roles admin/hr/user, verify each routes correctly

Add saveUserToFirestore() — only write if doc doesn't exist (first registration), use setDoc merge

Implement updateUserProfile(updates): updateDoc on users/{uid}, update profile sub-object

## Day 4 — Thu · Job List

Phase: User home screen — job listings & search

### Project Manager

Navigation complete sign-off — test all 3 role drawers work before proceeding

Clarify with team: job listings must show applicant count badge on each card (visible to all users)

Update Trello: Day 4 stories in progress — job listing, search, filter, job card component

Check team energy levels: 4 days in, is anyone struggling with blockers?

Prepare mid-project checkpoint questions for end of Week 1 review

### Scrum Master

Standup: confirm navigation story is DONE before moving forward

Pair UIUX1 (HomeScreen) with BE (getOpenJobs query) — they need to coordinate Firestore field names

Alert team: BE must create Firestore composite index for jobs (status=open + orderBy createdAt) or queries will fail

Timebox: HomeScreen layout by 12 PM, connect to Firestore by 3 PM, QA test by 5 PM

Create placeholder seed jobs in Firestore manually so UI team has data to work with immediately

### UI/UX Developer 1

Implement HomeScreen.js skeleton: search bar at top, filter chip row, FlatList for jobs, loading state

Build JobCard component: company initial avatar (colored square), job title, company name, location/type/salary meta row

Add status badge on JobCard (Open = green dot, Closed = red dot)

Add applicant count badge on JobCard: purple badge showing 'X applied' — visible to all users

Implement search filter in JS: filter jobs array by title, company, or location matching query string

### UI/UX Developer 2

Build type filter chips row: All, Full-time, Part-time, Contract, Remote — highlight active chip in navy

Implement pull-to-refresh: RefreshControl component wired to re-fetch jobs from Firestore

Implement empty state: briefcase icon + 'No jobs found' text + subtitle when list is empty

Add loading skeleton: 3 placeholder cards with grey shimmer while Firestore loads

Add job count label below filter chips: 'X jobs found' — updates reactively as filters change

### Backend Developer

Implement getOpenJobs(): Firestore query jobs where status=open, orderBy createdAt desc

Create composite index in Firebase console: jobs collection, status ASC + createdAt DESC

Add fallback getOpenJobs(): if index not ready, fetch all jobs and filter in JS

Implement getAllJobs(): same but no status filter — for HR dashboard

Seed Firestore with 8 sample jobs across Cebu, Manila, Davao with varied types and salaries

## Day 5 — Fri · Map

Phase: Job location map & detail modal with dropdowns

### Project Manager

Day 5 is the most technically complex day — map integration. Check in with BE and UIUX1 at 11 AM

Risk check: expo-location requires device permission prompt — ensure QA tests permission denial case

Update stakeholder: core job listing done, map feature in progress today

If map is blocked by API issues, authorize fallback: show city name text instead of map

Ensure team doesn't skip lunch — tight sprint, mental fatigue is a real risk

### Scrum Master

Standup: jobs list complete? If yes, unlock Day 5. If not, UIUX2 helps UIUX1 finish

Brief whole team on expo-location API: requestForegroundPermissionsAsync, getCurrentPositionAsync

Coordinate: UIUX1 builds map in JobDetailModal, BE adds lat/lng to job seed data simultaneously

Timebox map feature strictly: if not working by 2 PM, implement text fallback and move on

Update Trello — this is the biggest story point day; adjust if needed

### UI/UX Developer 1

Install expo-location: npx expo install expo-location and add plugin to app.json

In HomeScreen, request location permission on mount; store userLat/userLng in state

Implement JobDetailModal.js: slide-up modal with 3 collapsible dropdown sections (description, requirements, details)

Add Map section inside JobDetailModal: use react-native MapView (expo-maps or webview fallback), pin at job's lat/lng, user location pin in blue

Show distance from user to job: calculate with Haversine formula, display 'X km away' below company name on JobCard

### UI/UX Developer 2

Design and implement dropdown/accordion sections inside JobDetailModal: chevron icon toggles body

Build job summary card inside modal: company avatar (large), title, company, tags row (location/type/status), salary

Show applicant count prominently inside modal: 'X people have applied for this role'

Add 'Apply Now' section at bottom of modal with cover letter textarea and Submit Application button

Style modal header with close button (X), job title truncated, role-color background

### Backend Developer

Add lat, lng fields to all 8 seed jobs (use real Philippine city coordinates: Cebu 10.31/123.89, Manila 14.59/120.98, Davao 7.09/125.61)

Implement getJobsNearby(userLat, userLng, radiusKm): fetch all open jobs, filter by Haversine distance in JS

Add applicantCount field to each job document; increment on new application, decrement on withdrawal

Implement applyForJob(jobId, jobTitle, company, message): check duplicate, addDoc to applications, increment job applicantCount

Add serverTimestamp() to all Firestore write operations

## Day 6 — Sat · Apply

Phase: Apply flow, my applications & profile screen

### Project Manager

5 of 7 days done — Week 1 progress review: map done, auth done, listings done — on track

Verify apply flow requirement: user submits application → HR must see it in ManageApplications

Confirm profile screen is shared component used by all 3 roles (saves dev time)

Update risk log: applicantCount field syncing — flag for QA to stress test with multiple users

Plan Week 2 kickoff Monday: brief all team on HR + Admin tasks coming up

### Scrum Master

Standup: confirm map is done or fallback implemented before apply flow work starts

Coordinate UIUX2 (MyApplications) and BE (applyForJob backend) — they work in parallel today

Warn team: applyForJob must include duplicate check — QA will test applying twice to same job

Check burndown: if behind, descope MyApplications animation and focus on core functionality

Update Trello: Day 6 stories — Apply modal, MyApplications screen, Profile screen

### UI/UX Developer 1

Wire Apply Now button in JobDetailModal to applyForJob() from AppContext

Show ActivityIndicator on Submit button while Firestore write is in progress

On success: show Alert 'Application submitted! HR will review it soon.' then close modal

On error (already applied): show Alert 'You already applied for this job.' — no duplicate submission

Implement withdraw application: swipe-to-delete or Withdraw button on ApplicationCard with confirmation Alert

### UI/UX Developer 2

Implement MyApplicationsScreen.js: stat row at top (Total / Pending / Approved / Rejected count cards)

Build ApplicationCard: company avatar, job title, company name, status badge, applied date, message preview

Add filter by status in MyApplications: show All / Pending / Approved / Rejected tab chips

Implement ProfileScreen.js shared by all roles: hero with large initials avatar, role badge, editable fields below

Profile fields: Phone, Address/City, Bio, Skills, Experience, Education — show edit/save/cancel buttons

### Backend Developer

Finalize applyForJob(): duplicate guard via Firestore where query, return {success,error} object

Implement getMyApplications(): query applications where userId==currentUser.uid

Implement deleteApplication(appId): deleteDoc + decrement job applicantCount by 1

Implement updateUserProfile(updates): updateDoc users/{uid} with profile sub-object merge

Export all 6 new functions from AppContext; test each with console.log in a throw-away screen

## Day 7 — Sun · HR Dash

Phase: HR dashboard, post job & manage jobs

### Project Manager

Week 1 wrap-up review — demo full user flow to team: register → browse → map → apply → my apps

Confirm all 6 user-facing stories are marked Done in Trello before starting Week 2

Brief team on Week 2 plan: HR features Mon–Tue, Admin Wed, polish Thu–Fri, deploy Fri

Risk: HR and Admin screens share some Firestore functions with user screens — coordinate with BE

Send Week 1 summary to stakeholder: user flow 100% done, Week 2 = HR + Admin + polish

### Scrum Master

Run Week 1 retrospective: top 3 wins, top 3 issues, 3 process changes for Week 2

Update all Trello cards: user flow stories to Done, HR stories to sprint backlog

Confirm UIUX1 and BE coordination plan for HRDashboard: same getAllJobs() function, different UI

Week 2 standup time confirmed: 9 AM daily, same link

Remind team: Week 2 is faster pace — HR + Admin + Polish + Deploy in 7 days

### UI/UX Developer 1

Implement HRDashboardScreen.js: 3 stat cards (Total Jobs / Open / Closed) at top in purple

Build JobManageCard: company avatar (purple), title, company+location, type badge, applicant count badge

Add 3 action buttons per card: Edit (blue), Close/Reopen (toggle), Delete (red)

Implement EditJobModal: slide-up modal with pre-filled form, all fields editable, Save/Cancel buttons

Wire Edit, Delete, Toggle to updateJob() and deleteJob() from AppContext; show confirmation Alert on delete

### UI/UX Developer 2

Implement PostJobScreen.js: purple banner header, form card with all fields

Build job type chip selector: Full-time / Part-time / Contract / Remote as toggle row

Add live preview card below form: shows job title, company, salary, type badge as user types

Wire Post Job button to createJob() from AppContext; navigate to HRDashboard on success

Add field validation: title, company, and description are required — show inline error if empty

### Backend Developer

Implement createJob(jobData): addDoc with postedBy uid, status=open, createdAt, serverTimestamp

Implement updateJob(jobId, updates): updateDoc with spread updates + updatedAt timestamp

Implement deleteJob(jobId): deleteDoc — also delete all associated applications (batch or loop)

Confirm HR-only Firestore rule: only users with role=hr can write to jobs collection

getAllJobs() (no status filter) for HRDashboard; getOpenJobs() (status=open) for user HomeScreen — both exported

## Day 8 — Mon · HR Apps

Phase: HR application review — approve & reject

### Project Manager

Week 2 Day 1 kickoff — confirm team is rested and ready; review Week 2 Trello board

Priority check: HR approve/reject flow is the most critical business feature — protect this story

Confirm that when HR approves an application, the user's MyApplications status updates in real time

Verify Firestore security rules prevent users from changing their own application status

Mid-day check-in: is ManageApplicationsScreen on track for completion by end of day?

### Scrum Master

Standup: confirm all 7 Day 1–7 stories are done; if not, triage with PM immediately

Coordinate: UIUX1 builds ManageApplicationsScreen, BE implements updateApplicationStatus — sync field names

Set integration checkpoint at 3 PM: HR can successfully approve an application end-to-end

If ahead of schedule, add stretch goal: email notification or push notification on status change

Update Trello: HR approval story = highest priority for Day 8

### UI/UX Developer 1

Implement ManageApplicationsScreen.js: purple header, stat row (Total/Pending/Approved/Rejected)

Build filter tab chips: All / Pending / Approved / Rejected — filter applications list in JS

Build ApplicationReviewCard: applicant avatar (initial), name, email, job title badge, applied date

Show cover letter preview (3 lines, read-more expansion) inside ApplicationReviewCard

Wire Approve and Reject action buttons — Approve = green filled, Reject = red outlined; show confirmation Alert

### UI/UX Developer 2

Applicant count on HRDashboard JobManageCard should now reflect real applicantCount field from Firestore

Add sort options to ManageApplicationsScreen: newest first (default) / oldest first

Show review status in HR view: reviewed applications show 'Reviewed by you on [date]' label

Build empty state for ManageApplicationsScreen: people icon + 'No applications yet' message

Add loading state: ActivityIndicator while fetching applications list from Firestore

### Backend Developer

Implement getAllApplications(): getDocs from applications collection, sort by appliedAt desc

Implement updateApplicationStatus(appId, status): updateDoc with status + reviewedAt + reviewedBy

Implement getApplicationsByJob(jobId): query where jobId=={jobId} — for per-job HR view

Confirm Firestore rule: only HR role can write to applications.status field

Test approve flow: call updateApplicationStatus(id,'approved'), verify user's getMyApplications() reflects new status

## Day 9 — Tue · Admin

Phase: Admin panel — manage all users

### Project Manager

Admin panel is the final role to implement — confirm requirements: view all users, toggle active, change role, delete

Verify: when admin disables a user, that user gets kicked out on next auth state refresh

Confirm admin cannot delete their own account (safety rule)

Update timeline: admin + profile polishing = today; map refinement tomorrow; full polish Thu–Fri

Check with QA: are they running test cases daily or batching? Daily is strongly preferred

### Scrum Master

Standup: HR approval done? Confirm before admin work starts

Pair UIUX2 (ManageUsersScreen) with BE (getAllUsers, toggleUserActive, deleteUser) — coordinate today

Set integration test at 2 PM: admin disables a user, that user cannot log in

Remind team: admin must not see their own account in the delete list — add self-exclusion logic

Check burndown chart — 6 days left, admin + polish + deploy must all fit

### UI/UX Developer 1

Implement AdminDashboardScreen.js: stat grid (Total Users / Active / Disabled / HR Members / Job Seekers)

Add quick-action buttons in AdminDashboard: Go to Manage Users, View All Jobs (read-only list)

Show recent activity in AdminDashboard: last 5 registered users listed with role badge and join date

Add search bar in AdminDashboard to quick-find users by name or email

Wire all AdminDashboard data to getAllUsers() from AppContext; display computed stats from user array

### UI/UX Developer 2

Implement ManageUsersScreen.js: search/filter bar at top, FlatList of all users

Build UserManageCard: initials avatar (role color), display name, email, role badge, active status toggle

Add role change picker: TouchableOpacity showing current role → opens Alert with options: User / HR / Admin

Add Delete button (red trash icon) on each card with confirmation: 'This will permanently remove the user'

Add self-exclusion: hide the currently logged-in admin's own card from the delete/disable actions

### Backend Developer

Implement getAllUsers(): getDocs users collection, map to array with id

Implement toggleUserActive(userId, isActive): updateDoc isActive field; user blocked on next onAuthStateChanged

Implement deleteUser(userId): deleteDoc from users collection (does not delete Firebase Auth account — add note)

Implement updateUserRole(userId, role): updateDoc role field; user must re-login to get new drawer

Firestore rule: only admin role can read all users, only admin can delete user docs

## Day 10 — Wed · Map++

Phase: Map refinement, nearby jobs & available applicants display

### Project Manager

Admin done — 10 of 14 days complete. All 3 roles functional. Focus shifts to polish and extras

Confirm 'nearest job' feature: sort HomeScreen jobs by distance from user location (closest first)

Confirm 'available applicants visible' requirement: applicant count on job cards for all users

Scope check: is there time for push notifications or is that post-launch backlog?

Remind team: Thursday–Friday is polish + QA only; no new features after today

### Scrum Master

Standup: admin complete? All 3 role flows working end-to-end?

Coordinate: UIUX1 sorts job list by distance, BE provides sorted data or UIUX1 sorts in JS

Confirm applicantCount is live in Firestore (not just seeded) — BE verifies increment/decrement is working

Set stretch goal if time allows: show map overview screen with pins for all open jobs

Update Trello: last feature stories — nearby sort, applicant count live, map polish

### UI/UX Developer 1

Sort HomeScreen job list by distance: after fetching open jobs, sort array by distanceKm (Haversine) ascending

Show 'X km away' distance label on each JobCard under location meta

Add 'Nearest jobs' label at top of list when location permission is granted; 'All jobs' if denied

In JobDetailModal map section: add user location blue pin + job location red pin + distance label between them

Add animate-on-mount for modal: slide up smoothly using Animated.timing or react-native Animated API

### UI/UX Developer 2

Ensure applicantCount badge is consistently shown on all JobCard instances across the app

For HR's JobManageCard: show applicantCount with different label: 'X applicants' in purple

For job detail modal: bold the applicant count — 'X people have applied for this role' — above the apply section

Add map cluster behaviour: if multiple jobs in same city, show count bubble instead of individual pins

Polish HomeScreen header area: show 'Jobs near [detected city]' when location is available

### Backend Developer

Verify applicantCount increments correctly on applyForJob() and decrements on deleteApplication()

Run test: create 3 applications for same job → check applicantCount == 3 in Firestore

Implement getJobsSortedByDistance(userLat, userLng): fetch open jobs, compute distance per job, return sorted

Fix any composite index errors that surface from QA — check Firebase console for index suggestions

Add error boundary: if getOpenJobs() fails, return empty array not a crash — log error to console

## Day 11 — Thu · Polish

Phase: Full UI polish, error states & accessibility

### Project Manager

Feature freeze — no new features after today. Any new requests go to post-launch backlog

Run internal demo: PM demos entire app across all 3 roles to the full team

Collect UI polish notes in a shared doc — prioritize by visual impact

Confirm final presentation format: screen recording + live demo on device vs emulator

Review QA bug report from Days 1–10 — are all critical bugs resolved?

### Scrum Master

Standup: feature freeze confirmed by whole team — process change for today

Facilitate UI polish session: UIUX1 + UIUX2 work through polish checklist together

Ensure BE handles all error states gracefully — no unhandled promises or blank screens

Coordinate: QA runs full regression today while UIUX polishes — catch regressions immediately

Archive completed feature stories; create polish + bug-fix stories in Trello for today

### UI/UX Developer 1

Audit all screens for consistency: spacing, font sizes, border-radius, color usage match design system

Add loading skeleton shimmer on HomeScreen, ManageApplicationsScreen, ManageUsersScreen

Add micro-interactions: button press activeOpacity={0.85}, status badge pulse on Pending state

Fix all KeyboardAvoidingView issues on Login, Register, PostJob, and Apply cover letter textarea

Test every screen on both iOS and Android — fix any platform-specific layout differences

### UI/UX Developer 2

Run accessibility audit: all touchable targets min 44×44pt, all text min 12px, contrast ratio check

Add inline validation error messages under input fields (red text below field, not just Alert)

Ensure all empty states have icon + title + subtitle + optional CTA button

Polish sidebar/drawer: active route highlighted, smooth open/close animation verified on device

Update app.json: set correct splash screen color, app name 'JobFinder', icon configured

### Backend Developer

Wrap all Firestore functions in try/catch; return {success:false, error:e.message} on failure

Add Firestore security rules final review: test each rule in Firebase Emulator

Seed final demo dataset: 3 user accounts (admin@jobfinder.com, hr@jobfinder.com, user@jobfinder.com), 10 real-looking jobs, 5 applications in various statuses

Optimize: batch Firestore reads where possible; avoid N+1 queries (fetch applicantCount from job doc, not by counting application docs)

Write setup instructions in README.md: prerequisites, clone, npm install, firebaseConfig setup, expo start

## Day 12 — Fri · Bug Fix

Phase: Bug fixes, integration testing & performance

### Project Manager

Review QA bug report from Day 11 — triage with team: Critical bugs must be fixed today

Confirm: 0 critical bugs, max 2 high bugs acceptable for final demo

Prepare final demo script: 5-min walk-through covering all 3 roles sequentially

Check Firebase usage stats — confirm app is within Spark free tier limits

Confirm deployment plan for Day 14: Firebase Hosting for web version

### Scrum Master

Standup: how many critical bugs? Assign each to a specific person with deadline: today 3 PM

Facilitate bug triage meeting: UIUX + BE review QA bug list together — 30-min session, max

Set 3 PM code freeze for major changes — only targeted bug fixes after that

Confirm integration test scenarios with QA: 3 role end-to-end flows must all pass today

Update Trello: move all fixed bugs to Resolved; create Done column for today's fixes

### UI/UX Developer 1

Fix all Critical and High UI bugs from QA report: layout breaks, wrong colors, missing icons

Fix any navigation bugs: screens not dismissing, back button behavior incorrect

Verify apply flow on physical Android device — confirm cover letter textarea doesn't get hidden by keyboard

Fix map rendering issues if any: pin not showing, distance NaN for missing coordinates

Test drag-open of drawer on both hands — left-handed swipe on iOS, right-to-left on Android

### UI/UX Developer 2

Fix all accessibility bugs: small touch targets, missing labels, low contrast text

Polish register screen role selector: ensure selected state is visually distinct on all device themes

Fix any modal animation jank: test slide-up on older Android devices (API 28–30)

Ensure profile edit mode saves and reverts correctly — test cancel flow thoroughly

Final check: every screen title in the drawer header matches the screen's content purpose

### Backend Developer

Fix all Firestore-related bugs from QA: missing fields, wrong collection names, index errors

Run full integration test in Firebase Emulator: simulate all 3 user roles completing their flows

Verify Firestore security rules in production — not just emulator — test with REST API call

Performance check: measure time from login to HomeScreen displaying jobs — target under 3 seconds

Ensure demo seed data is clean: correct applicant counts, realistic job descriptions, valid coordinates

## Day 13 — Sat · Demo Prep

Phase: Demo preparation, README & final QA sign-off

### Project Manager

All bugs should be resolved or formally accepted as known issues with workarounds

Rehearse final demo presentation: time each section — target 8–10 min total with Q&A

Create presentation slides: problem statement, solution, architecture diagram, live demo, lessons learned

Confirm what hardware will be used for demo: phone + screen mirror, or web browser

Send calendar invite for final demo session (Day 14) to all stakeholders

### Scrum Master

Run final retrospective: what worked in 2 weeks, what slowed us down, what we'd do differently

Ensure all GitHub branches are merged to main; tag release v1.0.0

Verify README is complete: screenshots, setup steps, demo credentials, feature list

Archive all sprint Trello cards — screenshot board for project documentation

Confirm QA will give written sign-off today before deployment tomorrow

### UI/UX Developer 1

Record screen walkthrough video: user role flow — register, browse nearby jobs, open map, apply

Capture screenshots of every screen in light mode for README and presentation slides

Final check: app name shows 'JobFinder' in header (not 'MyDashboard' or default Expo app name)

Verify app icon and splash screen appear correctly on both iOS and Android

Test cold start: kill app completely, relaunch — verify login session persists (Firebase Auth persistence)

### UI/UX Developer 2

Record screen walkthroughs: HR flow (post job, review application, approve) and Admin flow (manage users)

Create annotated screenshots for presentation: callouts explaining each feature

Write feature list in README.md with bullet points matching project requirements

Final design consistency check: open every screen, compare against Day 1 Figma wireframes

Confirm all placeholder/test data has been replaced with realistic demo content

### Backend Developer

Deploy Firebase Hosting: expo export --platform web → firebase deploy

Set production Firestore security rules (not test mode) — no open read/write

Verify deployed web version works: open URL, login with demo credentials, all features functional

Document firebaseConfig.js setup in README — remind users to create their own Firebase project

Final Firestore health check: check usage metrics, confirm no unexpected read spikes

## Day 14 — Sun · Deploy

Phase: Final demo, deployment & project handover

### Project Manager

Deliver final stakeholder presentation: problem, solution, live demo, technical summary

Formally accept QA sign-off report as project completion evidence

Present lessons learned: what went well in 2-week sprint, what to improve

Hand over project deliverables: GitHub repo link, Firebase console access, README, QA report

Write project closure document and archive all project materials

### Scrum Master

Facilitate final team retrospective: each member shares one win and one lesson

Ensure GitHub repo is clean: only one commit per feature, descriptive commit messages, v1.0.0 tag

Hand over product backlog of post-launch ideas: push notifications, resume upload, employer profiles

Celebrate the team — 2 weeks, full app, 3 roles, map, Firebase. That is an accomplishment

Archive Trello board, standup notes, and all sprint artifacts for course submission

### UI/UX Developer 1

Live demo: present user role flow on physical device — show map, distance, apply in real time

Show before/after: Day 1 wireframe vs final implemented screen

Answer technical questions about React Navigation drawer setup and map integration

Submit GitHub repo link + web deployment URL as course deliverable

Reflect: write 1-paragraph personal summary of what you built and what you learned

### UI/UX Developer 2

Live demo: present HR and Admin role flows — post job, approve application, manage users

Walk through the design system: color choices per role, component reuse across screens

Show Figma prototype vs final app side by side

Submit your Figma file link as a design deliverable alongside the code

Reflect: document 3 design decisions you made and why (role colors, drawer layout, modal vs page)

### Backend Developer

Live demo of Firebase console: show Firestore collections (users, jobs, applications), explain schema

Show Firestore security rules: walk through role-based read/write restrictions

Confirm Firebase Hosting deployment URL is working and shareable

Submit: firebaseConfig template, Firestore schema diagram, security rules file as backend deliverables

Reflect: document how serverTimestamp, composite indexes, and security rules were implemented